## Contract Matrix
Contract Selection Matrix |  | Version: | v1 Sept 2024 | DISCLAIMER - The Local Buy contract selection matrix is intended as a general guide to assist in the initial selection of a Local Buy contract for a project. It is not a comprehensive system and does not consider all factors or issues that may be relevant to the project. Users must perform their own detailed assessment of the project and its specific requirements before finalising the choice of contract. The matrix should not be relied upon as the sole basis for determining which contract is appropriate
This Contract Selection Matrix will assist you in determining which type of contract to use for your project.
Enter the Project Name here: | [Insert Name of Project Here] |  |  |  | Please enter the name of your project here.
Question | Answer | Score | Comments
Complexity Criteria questions (X axis) |  | #N/A
Q1. Remoteness - Is the project to be done in a remote location? |  | #N/A |  |  | Please choose from the available drop down menu in column B to answer the question in Column A.
Q2. Does this project have long lead times for supplier of items? |  | #N/A |  |  | Your response will generate a score which will carry over the "Results of the Contract Selection Matrix" graph.
Q3. Are there materials that are supplied by the Principal? |  | #N/A |  |  | Please use the cell in Column D to make any notes you want.
Q4. Is there Level 1 Supervision (ie.AS3798)? |  | #N/A
Q5. Are there nominated Suppliers and Sub-Contractors? |  | #N/A
Q6. Is Design part of this Contract? |  | #N/A
Q7. Does this project have piling involved? |  | #N/A
Q8. Are there significant earthworks / inground works or undergroud works included in this contract? |  | #N/A
Q9. Are there any environmentally sensitive works or an environmentally sensitive site? |  | #N/A
Q10. Are there any Demolition work involved on this site? |  | #N/A
Contract Value questions (Y axis) |  | #N/A |  |  | Please ensure that you only say "YES" to only one of the options below and make sure the other options say "NO".
Is the value up to $250,000? |  | #N/A
Is the value between $250,000 and $1 Million? |  | #N/A
Is the value over $1 Million? |  | #N/A
Results of the Contract Selection Matrix
Contract Value
Up to $1 Million
Up to $250,000.00
Minor
Medium
Major

## Question List and Scores
Complexity Criteria
Question | Score | Question | Score | Question | Score | Question | Score | Question | Score | Question | Score | Question | Score | Question | Score | Question | Score | Question | Score
Q1. Remoteness - Is the project to be done in a remote location? |  | Q2. Does this project have long lead times for supplier of items? |  | Q3. Are there materials that are supplied by the Principal? |  | Q4. Is there Level 1 Supervision (ie.AS3798)? |  | Q5. Are there nominated Suppliers and Sub-Contractors? |  | Q6. Is Design part of this Contract? |  | Q7. Does this project have piling involved? |  | Q8. Are there significant earthworks / inground works or undergroud works included in this contract? |  | Q9. Are there any environmentally sensitive works or an environmentally sensitive site? |  | Q10. Are there any Demolition work involved on this site?
No, it is local. | 10 | No | 0 | No | 0 | No | 0 | No | 0 | No | 0 | No | 0 | No | 0 | No | 0 | No | 0
Yes, but within 100kms from head office | 15 | Yes | 10 | Yes | 10 | Yes | 10 | Yes | 10 | Yes | 10 | Yes | 10 | Yes | 10 | Yes | 10 | Yes | 10
Yes, it is over 100kms from head office | 20
Contract Value
Question | Score | Question | Score | Question | Score
Is the value up to $250,000? |  | Is the value between $250,000 and $1 Million? |  | Is the value over $1 Million?
No | 0 | No | 0 | No | 0
Yes | 40 | Yes | 80 | Yes | 100

## Data (hidden)
Password is
123456